## Sheet1
Week | Monday date | Weekly Milestones | Specific Tasks
1 | 2022-02-07 | Introduction | Kickoff meeting, read background material
2 | 2022-02-14 | github/individual orientation to project and data/start EDA | i) EDA w/ datamaid and any other EDA products; ii) github set-up; iii)individual project
3 | 2022-02-21 | EDA on hydro data sets/start with code | Ned's HI data and two current data sets
4 | 2022-02-28 | convert and test code
5 | 2022-03-07 | convert and test code
6 | 2022-03-14 | put into one document with simple workflow | Create Markdown doc w/ workflow
7 | 2022-03-21 | qaqc
8 | 2022-03-28 | improve on workflow and initial test with data sets
9 | 2022-04-04 | improve on code and workflow/qaqc
10 | 2022-04-11 | additional coding for any missing metrics or additoinal features we want to add
11 | 2022-04-18 | Complete draft markdown report
12 | 2022-04-25 | Prepare presentation & revise report
13 | 2022-05-02 | Submit final report and give presentation to NPS. Prepare Discovery Program showcase (blog or presentation)
May 6 showcase date
Formulas:
Monday date = [Monday date, row above]+7